## Sprint
|  |  |  | Week #1 (15 hrs / week) | [6 empty] | Week #2 (15 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 30 x 5) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23
|  |  |  | 150 | 135 | 120 | 105 | 90 | 75 | 63 | 54 | 45 | 36 | 27 | 18 | 9 | 0 | Ideal Burndown
|  |  | 150 | 150 | 133 | 120 | 104 | 91 | 78 | 74 | 72 | 57 | 45 | 33 | 16 | 4 | 0 | Remaining Hrs (Total)
Create basic game functionality (navigate across the map, kill monsters) | Design and Create World Map State Machine | Aashay | 15 | 15 | 11 | 6 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create advertisement video | Aashay | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tavern and Goblin Screen | Samkit | 6 | 6 | 6 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Textbox and Textbox main(Applying Singleton) | Samkit | 9 | 9 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Man And all Object Interaction | Samkit | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 3 | 2 | 0 | 0
| Game end Scene and Alignments | Samkit | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 0
| Worked on monster screen and man creation applied observer pattern for interaction | Aishwarya | 8 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implemented singleton gamestate to maintain gameplay score | Aishwarya | 7 | 7 | 5 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implemented MonsterFactory and created more monsters | Aishwarya | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 3 | 0 | 0 | 0
| Worked on weapon change functionality and gold accumulation alongwith randomization of monsters | Aishwarya | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 3 | 2 | 0 | 0 | 0
| created portals around the map and implemented man's interaction with portals | Harsh | 8 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Created singleton scoreboard on the top | Harsh | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Worked on Treasure Screen and Treasure Generation | Varshit | 7 | 7 | 6 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Worked on Treasure Chest and Weapon | Varshit | 8 | 8 | 7 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refine gameplay, improve design elements | Made map background and tooltip background transparent and fixed screen layout bugs | Harsh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 1 | 0 | 0
| Created startup screen on the start of the game | Harsh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 4 | 3 | 1 | 0 | 0
| Implement and apply Command Creations for player-object interactions | Aashay | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 6 | 6 | 2 | 0 | 0
| Game end Scene and Alignments | Aashay | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Implemented Treasure Factory for generating treasures and weapons | Varshit | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 5 | 2 | 1 | 0 | 0
| Worked on weapon man interaction | Varshit | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 5 | 3 | 1 | 0
Team:
Aashay | 15 hours / Week
Aishwarya | 15 hours / Week
Harsh | 15 hours / Week
Samkit | 15 hours / Week
Varshit | 15 hours / Week
Total Available Hours During Sprint: | 150